## Course_Progress
Demonstration | Topic | Start_date | End_Date | Remark
Theory and Explaination | Course Introductoin | 2025-01-06 | 2025-01-06
| Objective | 2025-01-06 | 2025-01-06
| Data Maturity Model | 2025-01-06 | 2025-01-06
| ETL-ELT | 2025-01-06 | 2025-01-06
| Data Warehouse, Data Lake, Lakehouse | 2025-01-06 | 2025-01-06
| Slowly Changing dimensions | 2025-01-06 | 2025-01-06
| DBT Overview | 2025-01-06 | 2025-01-06
| Common Table Expression | 2025-01-06 | 2025-01-06
Set up and Practice | Python Download and Installation | 2025-01-06 | 2025-01-07
| Snowflake account set up | 2025-01-06 | 2025-01-06
| dbt core installation | 2025-01-07 | 2025-01-07
| git installation and synchronization | 2025-01-07 | 2025-01-07
| Data Ingestion into snowflake for project | 2025-01-07 | 2025-01-07
| Project Overview | 2025-01-07 | 2025-01-07
| Dbt project initialization | 2025-01-07 | 2025-01-07
DBT Core - Topics | Models | 2025-01-08 | 2025-01-08
| Sources | 2025-01-08 | 2025-01-08
| Project Yml | 2025-01-08 | 2025-01-08
| Materializations - table and view | 2025-01-09 | 2025-01-09
| Source and ref keyword | 2025-01-09 | 2025-01-09
| Incremental Materialization - All types | 2025-01-09 | 2025-01-09
| Ephemeral materialization | 2025-01-09 | 2025-01-09
| Snapshots and SCD2 | 2025-01-13 | 2025-01-14
| Seeds | 2025-01-13 | 2025-01-13
| Tests | 2025-01-14 | 2025-01-14
| Macros | 2025-01-14 | 2025-01-14
| Custom Tests and packages | 2025-01-14 | 2025-01-14
| Dbt Documentation | 2025-01-15 | 2025-01-15
| Analyses | 2025-01-16 | 2025-01-16
| Hookups - Pre and Post | 2025-01-16 | 2025-01-21
| Exposures | 2025-01-21 | 2025-01-22
DBT - Deep dive | Debugging Test and Testing with dbt-expectations: | 2025-01-23 | 2025-01-24
| 1 - expect_table_row_count_to_equal_other_table | 2025-01-23 | 2025-01-23
| 2 - expect_column_values_to_be_of_type | 2025-01-23 | 2025-01-23
| 3 - expect_column_quantile_values_to_be_between | 2025-01-23 | 2025-01-23
| 4 - expect_column_max_to_be_between | 2025-01-23 | 2025-01-23
| 5 - expect_column_distinct_count_to_equal | 2025-01-23 | 2025-01-23
| 6 - Debugging dbt tests and working with regex | 2025-01-24 | 2025-01-24
| Debugging with logging | 2025-01-22 | 2025-01-22
| Using Variables | 2025-01-22 | 2025-01-23
| DBT Orchestration | 2025-01-24 | 2025-01-28
| Popular orchestration tool | 2025-01-24 | 2025-01-28
| Dagster orchestration toll | 2025-01-24 | 2025-01-28
| Accelerate dbt Development using power user for dbt core | 2025-01-29 | 2025-01-29
| Best Practices for dbt in production environment | 2025-01-29 | 2025-01-29
| DBT live production projects overview | 2025-01-29 | 2025-01-29
| Exercise for completing new dbt project | 2025-01-30 | 2025-01-30
| dbt Certification Exam Preparation Guide | 2025-01-30 | 2025-01-30
| Conclusion and Further Learning steps in data engineering projects | 2025-01-31 | 2025-01-31

## Sheet1
stg.src_review | 21st-oct-2021
1st sept 2021-1st oct 2021
int.fact_review | max(review_dt) = 20th-Oct-2021

## Sheet2
| raw_review | [5 empty] | customer_dime
| transactionid | cust_id | platform_id | amount | 2nd pary_id | update_dt | cust_id | custname | custcity
| 1 | 43 | upi | -45 | 67 | 2025-12-01 | 43 | anuj | del
| 2 | 12 | net bank | 87 | 64 |  | 12 | prerna | mum
| 3 | 45 | atm | -98 | 73 | 8th-jan | 45 | natrajan | ban
| 86730 | 67 | merchant | -34034 | 52 | 9th-jan-25 | 67 | chandraka | pune
98000
| 98001 |  |  |  |  | 10th
oh | 86730 | 67 | merchant | 34034 | 52 | 11th-jan | city
[7 empty] | 1 | del
[7 empty] | 2 | mum
| stg_bank | [5 empty] | 3 | ban
| 3 | 45 | atm | -98 | 73 | 8th-jan | 4 | pune
| 4 | 67 |  |  | 52 | 9th-jan-25
| 98000 | [5 empty] | review_id | STAR | revie_txt | create_dt | update_dt
| 98001 |  |  |  |  | 10th | 6738 | 1 | Awfull!! | 2nd jan | 2nd jan
[7 empty] | 6738 | 5 | Awful!! Update - I was not well it was very taks | 2nd jan | 10th-jan
[7 empty] | raw_review |  |  |  | review_dt
reviw_id
| fact_transaction | [5 empty] | 6738 | 5 | Awful!! Update - I was not well it was very taks | 2nd jan | 2nd jan
| transaction_id |  |  | update_dt
| 1 | [9 empty] | 9th jan
2
| 950328 |  |  | 7th-jan
[7 empty] | 6738 | 5 | Awful!! Update - I was not well it was very taks | 10th jan | 10th-jan
| 3 | 45 | atm | -98 | 73 | 8th-jan
| 4 | 67 |  |  | 52 | 9th-jan-25 | {{
| 98000 | [5 empty] | config(
| 98001 |  |  |  |  | 10th | materialized = 'incremental',
unique_key = 'id',
merge_update_columns = ['email', 'ip_address'],
...
|  |  | aws_s3 (raw) | stg_snowflake table | int_snowflake |  | )
}}
20240101_transaction.raw
|  |  | 20240102_transaction.raw | 1 month |  |  | select ... |  |  | create_dt | review_dt
|  |  | 20240103_transaction.raw |  |  |  | reviw_id
[7 empty] | 6738 | 5 | Awful!! Update - I was not well it was very taks | 10th - jan | 10th-jan
9th jan